## Sheet1
Enhanced Course Feedback System Dependencies
Work Package | Task | Dependency
Preliminary Work | PW1. Team Introduction
Preliminary Work | PW2. Architectural Design | PW1.
Preliminary Work | PW3. Technical Documentation
Preliminary Work | PW4. UI Design
Development/ FrontEnd Tasks | FRO1. Teacher Sign-In Page | PW3.
Development/ FrontEnd Tasks | FRO2. Feedback Request Form Page | PW3.
Development/ FrontEnd Tasks | FRO3. Student Feedback Form Page | PW3.
Development/ FrontEnd Tasks | FRO4. List of Previous Feedback Page | FRO1.
Development/ FrontEnd Tasks | FRO5. Admin Configuration Page | FRO2.
Development/ BackEnd Tasks | BAC1. Implement Authentication
Development/ BackEnd Tasks | BAC2. Course Management | BAC1.
Development/ BackEnd Tasks | BAC3. Feedback Management | PW3.
Development/ BackEnd Tasks | BAC4. Integration with ChatGPT API | PW3.
Development/ BackEnd Tasks | BAC5. Email Notification | BAC3.
Development/ Admin Configuration Tasks | ADMIN1. Configure University Authentication API
Development/ Admin Configuration Tasks | ADMIN2. Configure ChatGPT API
Development/ Admin Configuration Tasks | ADMIN3. Configure Email Server | PW3.
Security | SEC1. 48 Hour Time Limit
System Tasks | S1. Server Settings for performance needs | BAC3.
System Tasks | S2. Deployment | S1.
Non-Dev Tasks | ND1. PM
Non-Dev Tasks | ND2. TL | ND1.
Non-Dev Tasks | ND3. Non-Dev | PW3.
QA | ND4. Planning | PW3.
QA | ND5. Functional Testing | ND4.
QA | ND6. Regression Testing | ND5.
QA | ND7. Performance Testing | S2.
QA | ND8. Security Testing | S2.
Non-Dev Tasks | ND9. Bug Fix | ND2.

## Sheet2
Enhanced Course Feedback System Estimates
Task |  | Optimistic (hour) | Realistic (hour) | Pesimistic (hour)
Preliminary Work |  | 39 | 50 | 70
PW1. Team Introduction |  | 2 | 3 | 10
PW2. Architectural Design |  | 20 | 25 | 30
PW3. Technical Documentation |  | 5 | 7 | 10
PW4. UI Design |  | 12 | 15 | 20
Development |  | 89 | 114 | 162
Front-end
FRO1. Teacher Sign-In Page |  | 5 | 7 | 10
FRO2. Feedback Request Form Page |  | 5 | 9 | 12
FRO3. Student Feedback Form Page |  | 5 | 8 | 11
FRO4. List of Previous Feedback Page |  | 6 | 7 | 10
FRO5. Admin Configuration Page |  | 4 | 7 | 9
Back-end
BAC1. Implement Authentication |  | 7 | 8 | 13
BAC2. Course Management |  | 6 | 7 | 10
BAC3. Feedback Management |  | 8 | 9 | 11
BAC4. Integration with ChatGPT API |  | 8 | 10 | 13
BAC5. Email Notification |  | 6 | 9 | 12
Admin Configuration
ADMIN1. Configure University Authentication API |  | 8 | 10 | 16
ADMIN2. Configure ChatGPT API |  | 10 | 11 | 15
ADMIN3. Configure Email Server |  | 11 | 12 | 20
Security |  | 6 | 10 | 15
SEC1. 48 Hour Time Limit |  | 6 | 10 | 15
System Tasks |  | 12 | 18 | 26
S1. Server Settings for performance needs |  | 7 | 9 | 15
S2. Deployment |  | 5 | 9 | 11
Total Work |  | 146 | 192 | 273
ND1. PM | 0.2 | 29.2 | 38.4 | 54.6
ND2. TL | 0.2 | 29.2 | 38.4 | 54.6
ND3. Non-Dev | 0.05 | 7.3 | 9.6 | 13.65
ND4. Planning | 0.1 | 14.6 | 0.1 | 27.3
ND5. Functional Testing | 0.2 | 29.2 | 38.4 | 54.6
ND6. Regression Testing | 0.2 | 29.2 | 38.4 | 54.6
ND7. Performance Testing | 0.2 | 29.2 | 38.4 | 54.6
ND8. Security Testing | 0.2 | 29.2 | 38.4 | 54.6
ND9. Bug Fix | 0.25 | 36.5 | 48 | 68.25
Grand Total |  | 379.6 | 480.1 | 709.8

## Sheet3
Enhanced Course Feedback System Risk Register
# | Risk Source | Probability of Risk | Impact on the project if risk source happens | Impact areas | Status | Mitigation Plan
1 | Lack of Experience in Frontend Development | High | High | Project timeline, Frontend development progress | Not Occurred/In Progress | Provide training sessions for Satrio on frontend technologies.
2 | Backend Development Complexity | Moderate | High | Project timeline, Backend development progress | Not Occurred/In Progress | Conduct a thorough analysis of backend requirements before development begins.
3 | API Integration Issues | Moderate | Medium | Integration with university and ChatGPT APIs | Not Occurred/In Progress | Conduct early integration testing with university and ChatGPT APIs.
4 | Quality Assurance Bottleneck | Moderate | Medium | QA process, Project timeline | Not Occurred/In Progress | Implement an iterative testing approach with continuous feedback to Anna.
5 | E-mail Server Downtime | Low | Medium | Communication with teachers, Project timeline | Not Occurred/In Progress | Use a reliable e-mail service provider. Implement monitoring for server uptime.
6 | University Authentication API Issues | Moderate | High | Authentication process, Project timeline | Not Occurred/In Progress | Engage with university IT to validate API integration early in the project.
7 | Incomplete Feedback Summarization | Moderate | Medium | Feedback summarization accuracy, Project timeline | Not Occurred/In Progress | Conduct thorough testing of ChatGPT summarization before full implementation.